## Cover Sheet
PLAN OF ACTION AND MILESTONES (POA&M)
System Name | RHEL 9 Baseline
Scan Date | 2026-03-02
Date Generated | 2026-03-03
Source | DISA STIG
Total Findings | 4
CAT I (High) | 1
CAT II (Medium) | 2
CAT III (Low) | 1
Open Items | 4

## POA&M Findings
Weakness ID | Weakness Name | Point of Contact | Resources Required | Scheduled Completion Date | Milestone with Completion Date | Changes to Milestones | Source Identifying Weakness | Status | Category | Severity | Rule ID
POAM-001 | RHEL 9 must be configured so that the root account is not used for direct login. | John Smith | TBD | 2026-04-01 | Remediation in progress | None | STIG | Open | CAT I | HIGH | SV-257777r925318_rule
POAM-002 | RHEL 9 must display the Standard Mandatory DoD Notice before granting access. | John Smith | TBD | 2026-05-31 | Remediation in progress | None | STIG | Open | CAT II | MEDIUM | SV-257778r925319_rule
POAM-003 | RHEL 9 must enforce password complexity requirements. | John Smith | TBD | 2026-05-31 | Remediation in progress | None | STIG | Open | CAT II | MEDIUM | SV-257779r925320_rule
POAM-004 | RHEL 9 must send audit records to a different system or media than the system being audited. | John Smith | TBD | 2026-08-29 | Remediation in progress | None | STIG | Open | CAT III | LOW | SV-257780r925321_rule